DDR Progress

Background research and consultations

- Estimation of numbers and types of militia groups in Somalia developed from various sources (Status: initiated/ongoing)

- Collection and collation of previous documented experience on DDR and related activities in Somalia e.g. EC/GTZ, UNDP, UNESCO, etc. (Status: Completed)

- Informal consultations with all donors and agencies with experience on DDR or related activities in Somalia (Status: Completed)

- Attended consultations with Somali intellectuals, academics and others on critical issues facing Somalia, including disarmament and demobilization, held under the auspices of [tbc]. (Status: Completed)

Advisory inputs and technical assistance

- Prime Minister and Speak of Parliament provided short briefing and consulted on DDR issues (Status: Completed)

- Presentations on DDR lessons learned and recommendations on the way forward made to the Addis Planning Seminar (including panel discussions and question and answer), and the security sector working group of the AU Security Planning Workshop in Nairobi.  (Status: Completed)

- Familiarization session (1/2 day) given to 6-member Ministry of Defense delegation on DDR.(Status: Completed)

- Acted as technical advisor to a week-long planning session by the Ministries of DDR, National Security and Defense (organized under the auspices of SDPU).  Experience and key documents also shared with the group on DDR (e.g. model survey forms).

Strategy Development

- Dialogue opened with the Minister of DDR and his staff (Status: Ongoing)

- A draft strategy paper was developed by the inter-ministerial technical working group, and submitted to the three ministers (National Security, Defense and DDR) to inform next steps. (Status: Completed)

- A Concept paper on National DDR Commissions was developed and presented to the working group and Minister of DDR. (Status: Completed)