- Indicative Logical Framework Planning Matrix for the Education and Training Sector Somalia (One- year programme)                Rev. 3/2005

| - Intervention logic | - Performance Indicators | - Sources of verification | - Assumptions/ Risks |
| --- | --- | --- | --- |
| - Goal - To make a substantial contribution towards a structured government programme of development |  |  |  |
| - Purpose - Expanded and equitable access to quality and relevant education and training at all levels achieved |  |  |  |
| - Results |  |  |  |
| - R1 - Access to equitable quality basic education improved | - IR 1.1 Increased number of CEC/parent/PTA support learning spaces from .. to .. - IR 1.2 Increase in student enrolment from .. to .. in formal edu - IR 1.3 Increase in ABE / NFE learners from .. to .. - IR 1.4 Increase in NFE centres from .. to ... - IR 1.5 Number of textbooks printed/distributed/used in classrooms - IR 1.6 Increase of disadvantaged children in basic education - IR 1.7 Increase of female enrolment / participation in bas. edu. from .. to - IR 1.8 Increase in teachers recruitment from .. to . - IR 1.9 … number of teachers paid from Teachers Fund - IR 1.10 Increase in no. of teachers demonstrating child friendly methods from .. to .. |  |  |
| - R2 - Quality Secondary Education and TVET made more accessible to Somali youth of both sexes | - IR 2.1 Secondary enrolment increased to 25,000 by end 1st y. - IR 2.2 VTC enrolment increased to 8,000 trainees by end 1st y. - IR 2.3 Female enrolment in: secondary education: 40%, VET: 30% - IR 2.4 > 3,000 ex-combatants under training - IR 2.5 Relevant programmes for secondary and TVET are in place + addressing cross-cutting issues (gender, HIV/AIDS, peace, civic edu., environmental issues) - IR 2.6 TVET programmes + demobilisation plans re-oriented, in collaboration with private sector - IR 2.7 Work on common certification system (equivalent to international standards) for secondary and TVET introduced |  |  |
| - R 3 - Tertiary education sector- subject to separate planning workshop. - Indicative planning according to workshop, group 3: - Development plan for HE prepared and implementation started | - IR 3.1 Comprehensive needs assessment draft report completed - IR 3.2 Development plan circulated, stakeholders feedback incorporated and revised - IR 3.3 Core (at least 50% of MoHE) workforce recruited and introduced to job requirements (see also capacity building R 4) - IR 3.4 Students intake initiated (>50% of capacity) - IR 3.5 Development plan for national and intern. networking with HE institutions in place |  |  |
| - R 4 - Ministries of education (MoE + MoHE) established and fully operational | - IR 4.1 Staff recruited, equipment provided + utilised - IR 4.2 Ministries' core staff trained within first 6 months - IR 4.3 Capacity of edu. authorities at regional/district/community level built for supervision, monitoring + quality control - IR 4.4 Infrastructure rehabilitation plan developed and implementation started - IR 4.5 Equipment plan developed - IR 4.6 Quality assurance tools (e.g. EMIS) developed and staff trained in usage |  |  |
| - R 5 - Educational policies and plans for all sub- sectors developed and implementation started with adequate funding | - IR 5.1 Education survey expanded to all sub-sectors + school mapping completed (after 3 / 6 months) - IR 5.2 Country Sector Strategy paper developed + submitted at the end of year 1 - IR 5.3 Draft policies for all sub-sectors developed following consultative approach with stakeholders and (initial) implementation ensured - IR 5.4 Education plans for all sub- sectors developed - IR 5.5 Funding plan for sector in place (incl. local, national + intern. stakeholders) + budget approved |  |  |

Activities

Indicative Activity Schedule based on workshop discussions

| Ref. no. | Results and Indicative Activities | Responsibility | Year 1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 |
| R 1 | Access to equitable quality basic education improved | Dir. Gen. |  |  |  |  |
| 1.1 | Carry out national enrolment campaign | PR/Distr. Edu. Off. |  |  |  |  |
| 1.2 | Improve special education MOE management, prepare concept for advocacy of spec. education, and implement | Dir. Primary / Special Edu |  |  |  |  |
| 1.3 | Ensure learning spaces installed & functional – school construction rehabilitation temporary structures – tents | Dir. Admin |  |  |  |  |
| 1.4 | Provide learning materials, teacher guides + supplementary materials and ensure utilisation | Dir. Train. + Curr. |  |  |  |  |
| 1.5 | Ensure teachers are recruited, trained and adhere to quality instruction |  |  |  |  |  |
| 1.6 | Ensure teacher fund is established |  |  |  |  |  |
| 1.7 | Expand ABE/NFE programmes, collect & analyze ABE/NFE information, materials & experience |  |  |  |  |  |
| 1.8 | Establish new NFE centre |  |  |  |  |  |
| R 2 | - Access to sec. edu. and TVET for Somali youth improved |  |  |  |  |  |
| 2.1 | Strengthen policy regarding girls and vulnerable groups and provide fee concessions/waiver |  |  |  |  |  |
| 2.2 | Develop a pilot non - formal/alternative and outreach secondary education programme using ICT |  |  |  |  |  |
| 2.3 | Collect baseline data for secondary and develop EMIS/ school mapping |  |  |  |  |  |
| 2.4 | Expand and diversify TVET programmes through provision of syllabi, textbooks and instructor training for trades not covered so far. |  |  |  |  |  |
| 2.5 | Standardize teacher salaries, service conditions and school fees |  |  |  |  |  |
| 2.6 | Re-acquire/rehabilitate/equip post-primary public school facilities including libraries, laboratories etc. |  |  |  |  |  |
| 2.7 | New pre-service secondary TT extended to NE & C & S zones |  |  |  |  |  |
| 2.8 | 50% teachers in-serviced |  |  |  |  |  |
| 2.9 | 50% TB resources needs met |  |  |  |  |  |
| 2.10 | Complete common curriculum and assessment systems at 50% |  |  |  |  |  |
| 2.11 | Create / strengthen intermediary cadre for supervision, monitoring & quality control (at MoE and schools level) |  |  |  |  |  |
| 2.12 | Revise TVET programmes & training in collaboration with private sector & de- mobilization needs |  |  |  |  |  |
| 2.13 | Initiate resource mobilization strategies: Communication/mobilization advocacy targeting: communities, private sector, international community and religious leaders |  |  |  |  |  |
| 2.14 | Standardize teaching service conditions, salaries & school fees (MOE in consultation with stakeholders |  |  |  |  |  |
| 3. | - Development plan for HE prepared and implementation started - Tertiary education sector- subject to separate planning workshop. Indicative planning according to workshop, group 3 |  |  |  |  |  |
| 3.1 | Hire key staff |  |  |  |  |  |
| 3.2 | Equip offices |  |  |  |  |  |
| 3.3 | Hire technical assistance |  |  |  |  |  |
| 3.4 | Structure MOHE’s |  |  |  |  |  |
| 3.5 | Rent temporary office |  |  |  |  |  |
| 3.6 | Develop physical rehabilitation plan and start implementation |  |  |  |  |  |
| 3.7 | Carry out (rapid) needs assessment on status of higher education |  |  |  |  |  |
| 3.8 | Design EMIS for higher education |  |  |  |  |  |
| 3.9 | Prepare MOHE development Plan |  |  |  |  |  |
| 3.10 | Recruit/train staff (academic/non-academic) |  |  |  |  |  |
| 3.11 | Enrol/admit students |  |  |  |  |  |
| 3.12 | Initiate research and development activities |  |  |  |  |  |
| 4. | Ministries of education (MoE + MoHE) operational and functional |  |  |  |  |  |
| 4.1 | Put in place relocation plan including budget within 3 months |  |  |  |  |  |
| 4.2 | Ensure information on physical rehabilitation needs is available |  |  |  |  |  |
| 4.3 | Develop overall central and regional organisational structures and clarify roles |  |  |  |  |  |
| 4.4 | Ensure equipment is in place within 6 months |  |  |  |  |  |
| 4.5 | Develop operational plan & procedures |  |  |  |  |  |
| 4.6 | Set up HRD plan for MOE (for all sub- sectors) and Regional staff & implement |  |  |  |  |  |
| 4.7 | Prepare short term budget for MOE & regional offices, providing capital and operational cost |  |  |  |  |  |
| 5. | Educational policy and funding for all sub- sectors developed and implementation started |  |  |  |  |  |
| 5.1 | Develop networking with stakeholders in all sub sectors |  |  |  |  |  |
| 5.2 | Develop programmes and curriculum for all sub sectors |  |  |  |  |  |
| 5.3 | Undertake comprehensive education sector survey, including an inventory of organisations and interventions in the sector for all sub- sectors |  |  |  |  |  |
| 5.4 | Undertake school mapping |  |  |  |  |  |
| 5.5 | Ensure a programme quality assurance approach in all schools |  |  |  |  |  |
| 5.6 | Provide overall coordination to achieve an integrated policy of private and public schools |  |  |  |  |  |
| 5.7 | Design strategic planning for long- term data and EMIS collection |  |  |  |  |  |

Objectively verifiable indicators should be measurable in a consistent way and at an acceptable cost; they should be SMART: Specific, Measurable (quantitatively / qualitatively), Available at an acceptable cost, Relevant to the information needs, Time bound (so as to know when target to be achieved); many of the indicators in this logframe need to be concretised on the basis of further surveys /data collections and further planning.

This activity plan needs to be scrutinised and supplemented by the MoE and MoHE, once the lines of responsibilities and time requirements/constraints have been clarified; helpful is the introduction of critical milestones; once the input quantities (number of HR, time and quality level) are clarified, the Resource Schedule can be prepared, which will be the basis for budget requirements; see PCM Guidelines, pp. 85 – 91).