Itinerary plan arrangement for

Armoury consultant on 11th July 2005- 18 July 2005

A. Targeted Police stations/units for the assessment/training

- Bosaso (Bari region)

- Bartamaha Police station

- Biyo-Kulule Police station

- Bosaso Airport Police station

- Bosaso Seaport Police station

- Revenue collecting unit station

- Garowe (Nugal Region0

- Police emergency Unit station

- Regional Division Unit

- Burtinle District Police station

- Galkacyo (Mudug Region)

- Galkacyo-west Police station

- Galkacyo-east Police station

- Galkacyo Airport Police station

B. BAT training

- Each Police station/unit will identify two participants who will attend hands on components of BAT training. Total Trainees will be 22 individuals.

- Due to cost effectiveness and need to increase participation of the target trainees, it has been agreed that training will be conducted separately for each location, this will take one day per each location which is a total of three days.

- Participants will receive refreshment during the one day long training.

- Senior Police officer will be later nominated to accompany the armoury mission during their assessment/training.

- Training venue will be provided by the police in the respective regions

C. Logistics

- Vehicle Hire :

4daysx2vehiclesx80$ = 640 USD

3daysx1vehiclex50$ = 150 USD

Total              = 790 USD

*Fuel is inclusive for vehicle hire cost.

- Refreshment : 25personsx1dayx2$ = 50 USD

- Stationery : LS USD 70.

Grand total: USD 910.