PROPOSED WHO SUPPORTED COLLABORATIVE ACTIVITIES IN PUNTLAND STATE FOR 2000/2001

(Puntland Health Coordination meeting, Garowe 25/5/00)

- Prevention & control of Priority Communicable diseases:

- Cholera

- Support development of Cholera preparedness plans with concerned partners.

- Pre positioning of Cholera supplies

- Continue to provide lab support

- Support training in case management & prevention

- Support conduct of Post epidemic workshop

- TB

- Continue technical assistance & TB drugs supply support to TB centres at Bosaso, Gardo & Las Anod

- Advocate for implementing partners to start TB activities in Garowe & Galkaayo

- Malaria

- Support on going regional Malaria activities.

- Consultant will visit Puntland in June 00 for inception process of  Roll Back Malaria (RBM) program

- One Dr sent for 9 months fellowship course to Sudan to act as National focal point in future.

- HIV/AIDS/STD

- Continue support to labs by supplying lab kits & training for Blood safety.

- Support training in Syndromic management of STD

- Try to identify funding for procurement of STD drugs

- Emergency Preparedness

- Support conduct of training workshops on EP & Lab support to emergencies.

- Pre positioning of emergency supplies eg Meningitis vaccine

- Essential Drugs

- Support consultant to conduct trg (Dr Yacob Aden)

- EPI

- Support 2 trg workshops on EPI

- Construct Cold chain store at Garowe

4, Polio

- Conduct SNID in Bosaso with UNICEF with mopping up operations to stop wild virus circulation

- Conduct NID’s in Oct/Nov  with UNICEF

- Continue AFP surveillance

- HIS

- Support training in HIS

- Support MOSA in form of equipment for data entry & compilation.

- BDN

- Continue BDN project in present locations 1 dist + 3 villages

- Support expansion to 4 more villages

- Health Lab support

- Continue support to regional hospital labs

- Continue training of lab technicians

- Administration

- WHO is planning to establish a office in Garowe to facilitate closer working relations with MOSA.