DDR Summary Mission Report (Puntland) for ROLS Programme Manager

Policy/Strategy Development – Puntland authorities continue to need more time to consult internally and develop coherent policy positions following the first facilitated discussion on the matter, especially with the absence of the Darawishta.  It was agreed that the Task Force would convene again on 26 May.  A consultant may be engaged to support policy development for a finite period of time pending wider recruitment (I would like to discuss this with you).

Final Registration- Completion of the registration of the Darawishta has been planned, and agreed by the Task Force, but the Darawishta must endorse the move.  A letter will be sought from the Chief of Staff on this issue.  When approved, the logistics and administration will completed so the exercise can start 1st week of June.

Capacity building for Government- Broadly agreed to move forward with structure and posts for Government DDR Unit.  I’ve proposed that it be small (4-5 people).  On my return ToRs, and a Business Plan, will be developed.  In addition, equipment (5 computers, 2 printers, etc.), operations and transport support will be provided.  A training event is expected to take place

- Support to Staffing, including the following based on the rates set by Mine Action, and recruited and monitored on a service basis:

  - Technical Advisor/Coordinator

  - Database Operator

  - Monitors/Community Relations (x2)

  - Liaison Officers - Police and Darawishta (x2)

  - Finance/Logistics Assistant

DDR Unit Premises – The engineer has carried out an assessment and will be providing a bill of quantity within the next week for DDR premises in the PMAC compound.  A four-room complex is envisaged near the DG’s office.

Socio-Economic Survey to Prepare Reintegration- The study will be initiated by ILO in June.  The Puntland authorities strongly support this work to ensure sustainability of reintegration.  In addition to improving the design of our packages, this initiative will protect UNDP from the recriminations suffered by UNESCO.

UNDP DDR Office Set Up - The ROLS/DDR component will set up in the back offices of the UN Compound.  Recruitment is underway for three ROLS/DDR posts.   The National Professional and National Officer have been short listed and interviews are now planned, while the Finance/Logistics Officer has been selected and is being put forward to HR for the position.   Computers have been requested (3 plus a printer), but have not yet been provided.  A vehicle has also been requested.

11 May 2005