The Transitional Federal Government (TFG): Immediate Relocation Priorities

8 February 2005

SUMMARY TOTAL OF TFG PRIORITY REQUIREMENTS FOR 2-6 MONTHS

| No. | Component | Funding requirement |  | Contribution / Pledges |  | Shortfall |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Euro € | USD $ | Euro € | USD $ | Euro € | USD $ |
|  | Relocation and Logistics | 1,568,616 | 2,039,201 | 311,667 | 405,167 | 1,256,949 | 1,634,034 |
|  | Reconciliation, Peacebuilding and the Establishment of Regional and District Administrations | 6,169,800 | 8,020,740 | 0 | 0 | 6,169,800 | 8,020,740 |
|  | DDR of Militias | 17,925,600 | 23,303,280 | 2,307,692 | 3,000,000 | 15,617,908 | 20,303,280 |
|  | Police Force Formation | 31,455,845 | 40,892,598 | 3,523,082 | 4,580,006 | 27,991,844 | 36,389,397 |
|  | TOTAL | 57,119,861 | 74,255,819 | 6,142,441 | 7,985,173 | 50,977,420 | 66,347,451 |

Matrix 1: Relocation and Logistics Plan

[Reference RAP section Support to Transitional Federal Institutions, Project 1-2]

| No. | Item Description | Funding requirement |  | Contribution / Pledges |  | Shortfall |  | Donor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Euro € | USD $ | Euro € | USD $ | Euro € | USD $ |  |
|  | Relocation cost of 987 delegates of the Somali National Reconciliation Conference (SNRC) from Nairobi to Somalia. | 379,616 | 493,501 | 157,821 | 333,501 | 221,795 | 160,000 | EC/GoK |
|  | Relocation stipend for Cabinet & MPs – one time cost. | 687,500 | 893,750 | 0 | 0 | 687,500 | 893,750 | - |
|  | Establishing of TFG Liaison Offices. | 501,500 | 651,950 | 153,846 | 200,000 | 347,654 | 451,950 | Norway |
|  | TOTAL | 1,568,616 | 2,039,201 | 311,667 | 405,167 | 1,256,949 | 1,634,034 |  |

Matrix 2: Peacebuilding, Reconciliation and Establishing Regional and District Administrations

| No. | Item Description | Funding requirement |  | Contribution / Pledges |  | Shortfall |  | Donor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Euro € | USD $ | Euro € | USD $ | Euro € | USD $ |  |
|  | Accommodation, transportation, security staff, rental of facilities, logistics and other management expenses (92 conference x100 participants x 60 days) | 4,416,000 | 5,740,000 |  |  | 4,416,000 | 5,740,000 |  |
|  | Participation of Federal Transitional Parliament MPs in the reconciliation activities at district and regional level (per diems -275x60 daysx70 Euros, transportation, security) | 1,305,000 | 1,696,500 |  |  | 1,305,000 | 1,696,500 |  |
|  | High level Ministerial coordination, monitoring and assisting in the reconciliation conferences in 4 zones | 290,000 | 377,000 |  |  | 290,000 | 377,000 |  |
|  | Key district stakeholders support to mobilization at district level (92 district x10 individuals x 15 Euro x 60 days) | 828,000 | 1,076,400 |  |  | 828,000 | 1,076,400 |  |
|  | Security enhancement, reconciliation and formation of 14 regional administrations (during the regional conferences) | 450,000 | 585,000 |  |  | 450,000 | 585,000 |  |
|  | Management and technical support expenses at regional level (3 administrative staff at the Ministry of Reconciliation and Finance) | 10,000 | 13,000 |  |  | 10,000 | 13,000 |  |
|  | Awareness raising | 1,000,000 | 1,300,000 |  |  | 1,000,000 | 1,300,000 |  |
|  | Contingency | 293,000 | 381,940 |  |  | 293,000 | 381,940 |  |
|  | TOTAL | 7,764,800 | 10,094,2408 | --- | --- | 7,764,800 | 10,094,2408 |  |

Matrix 3: Militia DDR

| No. | Item Description | Funding requirement |  | Contribution / Pledges |  | Shortfall |  | Donor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Euro € | USD $ | Euro € | USD $ | Euro € | USD $ |  |
|  | Establishing Institutions, capacity building and operations | 241,000 | 313,300 |  |  |  |  |  |
|  | Registration, screening and reinsertion assistance (53,000 ex-combatants) | 11,742,000 | 15,264,600 |  |  |  |  |  |
|  | First Phase Reintegration (7,000 initial target group) | 4,307,600 | 5,599,800 |  |  |  |  |  |
|  | Weapons and Ammunition management | 951,200 | 1,236,560 |  |  |  |  |  |
|  | Awareness raising and monitoring of DDR and weapons surrender | 683,800 | 888,940 |  |  |  |  |  |
|  | TOTAL | 17,925,600 | 23,303,280 | 2,307,692 | 3,000,000 | 15,617,908 | 20,303,280 | EC, Sweden, UNDP (CO and HQ), UNESCO |

Matrix 4:  Police Force Formation (6 months)

[Reference RAP section Support to Transitional Federal Institutions, Project 1]

| No. | Item Description | Funding requirement |  | Contribution / Pledges |  | Shortfall |  | Donor |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Euro € | USD $ | Euro € | USD $ | Euro € | USD $ |  |
|  | Training | 966,153 | 1,256,000 | 769,238 | 1,000,000 | 256,000 | 196,923 |  |
|  | Rehabilitation and Equipment of Police Infrastructure | 9,860,770 | 12,819,000 | 1,923,077 | 2,500,000 | 7,937,692 | 10,319,000 |  |
|  | Operational Equipment (Vehicles and Communications) | 9,847,693 | 12,802,000 | 769,230 | 1,000,000 | 9,078,462 | 11,802,000 |  |
|  | Police Salaries | 5,598,306 | 7,277,799 | --- | --- | 5,598,306 | 7,277,799 |  |
|  | Police EOD teams (Clearance of UXOs) | 1,592,153 | 2,069,800 | 15,384 | 20,000 | 1,576,769 | 2,049,800 |  |
|  | Custodial service (re-establishment of prison service and rehabilitation of infrastructure) | 3,590,770 | 4,668,000 | 46,153 | 60,000 | 3,544,615 | 4,608,000 |  |
|  | TOTAL | 31,455,845 | 40,892,598 | 3,523,082 | 4,580,006 | 27,991,844 | 36,389,397 | EC, Denmark, Norway, UNDP (CO, HQ) |

The conversion is $1.3 USD  to  € 1.00 Euro

TFG Relocation plan calls for initial support for logistics.  Further requirements will be elaborated as related to Support to Transitional Federal Institutions.

The conversion is $1.3 USD  to  € 1.00 Euro

Reconciliation will occur over a 2 month period.

The conversion is $1.3 USD  to  € 1.00 Euro

The conversion is $1.3 USD  to  € 1.00 Euro

The conversion is $1.3 USD  to  € 1.00 Euro